## TestStatus
LISr-ISP ES2評価項目表
項目No | 大項目 | 中項目 | 小項目 | 詳細項目 | 测试方法 | Status 2025/06/13 ChipNo.002: on IC socket ChipNo.003 : SMT on board | Status 2025/06/17 ChipNo.004 : SMT on board (ChipNo.003 is broken and has been sent to Lu-san for repair) | Status 2025/06/17 ChipNo.004 : SMT on board (ChipNo.003 is broken and has been sent to Lu-san for repair) | Status 2025/06/23 ChipNo.004 : SMT on board (ChipNo.003 is broken and has been sent to Lu-san for repair) | Description | 测试版本
1 | Chip itself check | measure impedance of each pin before power on | Open-Short impedance |  | ICソケット版評価ボード上で全端子の抵抗、GNDと電源端子の短絡、開放などをマルチメータにて測定 | OK | Same as No.3 | Same as No.3 | OK
2 |  | power on each power domain step by step | Voltage( 7 domain ) ripple time chart Power ON sequence Power OFF sequence |  | 各電源の立上り順番と時間をオシロスコープにて測定。 （起動シーケンスは以下の通り） 3.3V->1.8V->1.1V->2.5V->1.2V-> DDR4_VREFCA_PHY0 &1, DDR4_VTT_PHY0 &1->Reset | OK | Same as No.3 | Same as No.3 | OK
3 |  | CLK function check | 27MHz on board OSC EXT input CLK from Cam module path |  | 27MHzOSCクロック波形をオシロスコープにて測定 | OK | Same as No.3 | Same as No.3 | OK
4 |  | RESET function check | POR timing and delay Manual reset sw |  | リセット回路動作確認 | OK | Same as No.3 | Same as No.3 | OK
5 |  | JTAG and SWD connection check | JLINK Keil |  | JLINK（JTAG)、KeilツールによるSWD接続確認 | OK | Same as No.3 | Same as No.3 | OK
6 |  | communication port reset status check | MIPI TX MIPI RX UART SPI I2C AutoFocus |  | reset status check of each IF ( MIPI TX/RX,UART , SPI, I2C ,AF) | OK | Same as No.3 | Same as No.3 | OK
7 | running internal boot ROM | Boot mode pin function check | Boot SRAM |  | UARTにて各起動用Bin Fileのダウンロード確認 BootPinの設定により4種類の起動Mode動作を確認 | OK | Same as No.3 | Same as No.3 | OK
|  |  | Boot Flash |  |  | OK | Same as No.3 | Same as No.3 | OK
|  |  | Boot FlashCache |  |  | OK | Same as No.3 | Same as No.3 | OK
|  |  | Debug |  |  | OK | Same as No.3 | Same as No.3 | OK
8 |  | “UART command” boot mode check | app bin update |  | UARTにてapp bin Fileのダウンロード確認 UART Command 機能を確認 | OK | Same as No.3 | Same as No.3 | OK
|  |  | flash cfg update |  | UARTにてflash cfg Fileのダウンロード確認 Flash設定機能を確認 | OK | Same as No.3 | Same as No.3 | OK
9(1) | after boot loader running | device driver function check | cache/Flash | register read and write | Traverse the read and write of all registers | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | mode selection support | Data transmission in different transmission modes | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | master and slave mode support | has no test condition for SLAVE mode | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | selectable serial interface mode support | Configure QSPI to interact with flash | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | sample delay time configurable | Configure the number of delay clocks for sampling time | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | sample mode configurable | Configure clock for data transmission under different Polarities and Phases | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | baud rate configurable as master | Configure clock for data transmission at different baud rates | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | fifo depth configurable | configure FIFO receive and send thresholds | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | interrput support | Check if the interrupt has entered,In interrupt testing, it has been covered | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | support configurable single, dual, quad and octal mode | Data transmission in different SPI frame formats | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | configurable command, address length, wait cycle and transmission data size | Check if the instruction, address, waitcycle, and data waveform output by QSPI are correct | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | support skip address and command phase at enhanced spi mode | Check if the QSPI output waveform is correct | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | xip support | Check if the data in the memory mapping area is correct | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | cache configurable support | Check cache hit count | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | flash write + flash read (single) | Use single line mode for read-write testing | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | xip+cache on (fast quad) | Test using xip+cache on mode | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | xip+cache off (fast quad) | Test using xip+cache off mode | OK | Same as No.3 | Same as No.3 | OK
9(2) |  |  | UART | UART transmit/receive | Configure UART and complete basic data reading and writing | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | UART baud rate | Configure UART with different baud rates for data transmission and reception | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | UART interrupt | Confirm sending and receiving interrupts.In interrupt testing, it has been covered | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | UART loopback | Confirm loopback mode data transmission and reception | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | UART fifo | Confirm that the FIFO function is normal | OK | Same as No.3 | Same as No.3 | OK
9(3) |  |  | I2C | i2c transmit/receive | Configure registers to complete basic data transmission and reception | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | i2c interrupt | Enable interrupt register, confirm triggering is normal.In interrupt testing, it has been covered | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | i2c three speeds | Configure different rates to confirm data transmission and reception | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | i2c matser/slave | Configure slave mode and confirm data transmission and reception | OK | Same as No.3 | Same as No.3 | OK
9(4) |  |  | SPI | spi transmit (as master) | SPI sending/receiving data | note ==> see description | Same as No.3 | Same as No.3 | note ==> see description | Data loss when SPI master writing to FIFO continually. Temporary countermeasure: each data access with enough delay. SPI master is not used in LiSoC. same as ES1,
|  |  |  | spi receive (as slave) | SPI sending/receiving data | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | spi operation mode | SPI Motorola/TI mode | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | spi fifo status | FIFO empty full state and related interrupt situations | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | spi clock phase and polarity | The Phase and Polarity of SPI Clock | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | spi clock rate | Different clock frequencies for sending/receiving data in SPI | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | spi interrupt | SPI's interrupt function,In interrupt testing, it has been covered | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | spi slave/master mode | Configure SPI mode and confirm data transmission and reception | OK | Same as No.3 | Same as No.3 | OK
9(5) |  |  | WDT | WDT interrupt | When WDT timeout occurs, interrupt is reported | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | WDT reset | When WDT timeout occurs, there will be a WDT reset | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | WDT pause | By setting, WDT can be paused | OK | Same as No.3 | Same as No.3 | OK
9(6) |  |  | RTC | RTC basic function | RTC Basic Function Configuration and Testing | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | RTC Pre-scaler | Modify Pre-scaler and confirm the RTC trigger time | OK | Same as No.3 | Same as No.3 | OK
9(7) |  |  | TIMER | TIMER basic function | Check if the time from timer startup to interrupt generation is consistent with the setting | NG | Same as No.3 | Same as No.3 | NG | The timer timing is unstable [chenxy,25-06-24] The timer function is cpu-subsystem embedded function, not a mandatory function required by lisoc normal operation.
|  |  |  | Timer 2 work mode, free running /individual running | Check that the free running/standalone running mode is working properly。 | OK | Same as No.3 | Same as No.3 | OK
9(8) |  |  | GPIO | GPIO basic function | Configure registers and check the corresponding PAD values The value of force PAD and check the corresponding register | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | GPIO interrupt check | Check if the interrupt has entered | OK | Same as No.3 | Same as No.3 | OK
9(9) |  |  | INTERRUPT | Uart0_irq | Configure the initialization parameters, enable interrupts, and confirm that the interrupt function can trigger them | OK | Same as No.3 | Same as No.3 | OK | cahe_irq cannot be triggered,same as ES1, Some new IRQs added to ES2 have not been tested yet 2025/06/17 Mipi_rx_err_ecc_irq/Mipi_rx_err_cs_irq haven't been triggered yet, so I haven't thought of any good triggering conditions. The interrupt of cache is the same as es1, and I don't know how to trigger it.
|  |  |  | Uart1_irq |  | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | Spimst_irq |  | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | Spislv_irq |  | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | qspi_irq |  | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | rtc_irq |  | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | wdt_irq |  | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | gpioa_irq |  | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | gpiob_irq |  | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | Timer0_irq |  | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | Timer1_irq |  | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | Timer2_irq |  | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | I2c0_irq |  | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | I2c1_irq |  | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | I2c2_irq |  | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | Isp_irq |  | not tested yet | OK | OK | OK
|  |  |  | Cache_irq |  | NG | ? | ? | ?
|  |  |  | Mipi_rx_err_ecc_irq |  | not tested yet | ? | ? | ?
|  |  |  | Mipi_rx_err_cs_irq |  | not tested yet | ? | ? | ?
|  |  |  | AF_CMPL_Handler |  | not tested yet | OK | OK | OK
|  |  |  | MIPI_RX_HERR_OUT_Handler |  | not tested yet | OK | OK | OK
|  |  |  | MIPI_RX_VERR_OUT_Handler |  | not tested yet | OK | OK | OK
9(10) |  |  | CLK | RESET | Read the default register initial value of each module, then modify it to 0xFFFFFFFF and reset RCC, and confirm whether the module registers have been restored to their initial values | OK | Same as No.3 | Same as No.3 | OK | 2025/06/18 The original frequency divider is still incorrect, and the backup frequency divider has been improved by modifying the 1.1V voltage. The soldering board is okay, but the socket board 297M is unstable
|  |  |  | rcc gate | Set the RCC gate register and confirm if there is a gate | OK | Same as No.3 | Same as No.3 | OK
|  |  |  | mco | Set the MCO register and confirm if the clock frequency is correct | NG | Same as No.3 | Same as No.3 | NG
|  |  | GPIO | PINMUX | Configure AF to be reused as the corresponding IO | OK | Same as No.3 | Same as No.3 | OK
9(12) |  |  | sysreset |  | Check if the sysreset function can reset the MCU through serial port output | OK | Same as No.3 | Same as No.3 | OK
10(1) | registerR/W test of user defined IP | ISP |  |  | Traverse test for reading and writing module registers | OK | Same as No.3 | Same as No.3 | OK
10(2) |  | CCHG |  |  |  | OK | Same as No.3 | Same as No.3 | OK
10(3) |  | LISr |  |  |  | OK | Same as No.3 | Same as No.3 | OK
10(4) |  | MIPI RX |  |  |  | OK | Same as No.3 | Same as No.3 | OK
10(5) |  | MIPI TX(2.5G) |  |  |  | OK | Same as No.3 | Same as No.3 | OK
10(6) |  | TPG |  |  |  | not tested yet | OK | OK | OK
10(7) |  | Auto Focus |  |  |  | not tested yet | OK | OK | OK
18 | IP function check | DDR0 and DDR1単体test | BIST |  | Call the test function bist_op() provided by the IP ip vendor to confirm the test results | OK | Same as No.3 | Same as No.3 | OK
|  |  | R/W from CPU |  | Perform random number read-write testing on DDR and confirm if the read-write results are consistent | OK | Same as No.3 | Same as No.3 | OK | No.3 welding plate is OK.ES2 has been resolved No.2 socket board is unstable
|  | AutoFocus | VCM |  | communicate with VCM driver LSI by test program , check LSI signals | not tested yet | OK | OK | OK | Please refer to the No9 sheet for details The current output by the sensor meets expectations
|  |  | Stepper |  | communicate with Stepper driver LSI by test program , check LSI input and output signals | not tested yet | NG | NG | OK | Please refer to the No9 sheet for details AF0~AF4/AF_CLK/AF_COUNT is ok.
|  | MIPI_RX/TX_THRU |  |  |  |  | NG | NG | ? | Please refer to the No10 sheet for details UHD30/FHD60 THRU is OK. UHD60 is uncertain whether it is unsupported or configured incorrectly, there are still issues at present
|  | TPG |  |  | set several configuration by test program | not tested yet | NG | NG | ? | Please refer to the No11 sheet for details The current register operation status of TPGEN is normal, and it needs to be confirmed whether the output image is correct
19 | data path | Video data path combination test | imx415_FHD60_RAW12_YUV422_8 |  | 1）Download each configuration files 2）checking MIPI display device result ( Test BOX or ROCK5B ) |  |  |  | OK(F22 MAX and ROCK 5B) | with Test BOX ( Dothinky F22 MAX ) , not tested yet with ROCK5B No.3 welding plate is OK No.2 socket board : have some noise this issue under investigating 2025/06/23 The welding board is OK under the backup frequency divider, but the socket board's backup frequency divider of 297M is still unstable. Rock5b still hasn't figured out 10 bit and UHD60 yet
|  |  | imx415_FHD60_RAW12_YUV422_10 | [5 empty] | OK | same as above
|  |  | imx415_FHD60_RAW12_RGB888 | [5 empty] | OK(F22 MAX and ROCK 5B) | same as above
|  |  | imx415_UHD30_RAW10_YUV422_8 | [5 empty] | OK(F22 MAX and ROCK 5B) | same as above
|  |  | imx415_UHD30_RAW10_YUV422_10 | [5 empty] | OK | same as above
|  |  | imx415_UHD30_RAW10_RGB888 | [5 empty] | OK(F22 MAX and ROCK 5B) | same as above
|  |  | imx415_UHD30_RAW12_YUV422_8 | [5 empty] | OK(F22 MAX and ROCK 5B)
|  |  | imx415_UHD30_RAW12_YUV422_10 | [5 empty] | OK
|  |  | imx415_UHD30_RAW12_RGB888 | [5 empty] | OK(F22 MAX and ROCK 5B)
|  |  | imx415_UHD60_RAW10_YUV422_8 | [5 empty] | OK | same as above
|  |  | imx415_UHD60_RAW10_YUV422_10 | [5 empty] | - | Not supported, frequency exceeded
|  |  | imx415_UHD60_RAW10_RGB888 | [5 empty] | - | Not supported, frequency exceeded
|  |  | imx415_vga_xx | a |  |  |  |  | - | The sensor is not supported
|  |  | imx415_UHD60_RAW10_YUV422_8 long time testing | [5 empty] | OK | Running for 16 hours without any issues.（297M/324M is OK.）
|  | AE/AWB |  |  | 1）Read White background value and stored into ae/awb memory 2）write each gain value 3）watch display effect | not tested yet | not tested yet | OK | OK | The measurement and calculation results are consistent with es1
|  | DEBUG0-7 |  |  | Observe whether the synchronization signal is normal using an oscilloscope | not tested yet | not tested yet | OK | OK | Please refer to No.12 for the measurement results
|  | DQ16 |  |  | Enable DQ16 and observe the output image |  |  |  | ? | See no13 for details
|  | interlace | [6 empty] | - | The sensor is not supported
|  | mipi lane swapping |  |  | Modify the order of mipi lan and observe whether the image output is normal | not tested yet | not tested yet | OK | ? | See no13 for details

## Chip test results
Test items with known issues are not considered NG items
1 | timer | Both socket board and soldering board exist
2 | DDR | Only socket board exists
3 | UHD60 long time | Only socket board exists
4 | UHD60 mipi rxtx thru | Both socket board and soldering board exist
5 | Backup frequency divider jitter | Only socket board exists
6 | Original frequency divider error | Both socket board and soldering board exist
No. | BOOTROM | JTAG | Peripheral | DataPath（测量5分钟） | Remarks
1 | NG | NG | NG | NG | I accidentally damaged the chip
2 | PASS | PASS | PASS | PASS
7 | PASS | PASS | PASS | PASS
8 | PASS | PASS | PASS | PASS
13 | PASS | PASS | PASS | PASS
14 | PASS | PASS | PASS | PASS
15 | PASS | PASS | PASS | PASS
16 | PASS | PASS | PASS | PASS
17 | PASS | PASS | PASS | PASS
18 | PASS | PASS | PASS | PASS
19 | PASS | PASS | PASS | PASS

## debug history
No | Date | status | Module | Error Description | 原因分析及对策 | #1 | #2 | #3
1 | 2025-06-06 | OnGoing | datapll clk | FHD60/UHD30 case运行的时候，lisr寄存器和cchg寄存器报错 | 定位到datapath clock异常。详细参见No1 sheet 具体来说就是原分频器的“11/48”分频支路不能正常工作，变成了“1/4”。因此无法生成{148.5, 297, 74.25}MHz等频率。
2 | 2025-06-06 | OnGoing | datapll clk | 备用分频器抖动 (1) 焊接板，148.5MHz，不抖 (2) 焊接板，297MHz，抖，且频率不对 (3) Socket板，148.5，抖 （但是mipi-rx不接时不抖） (4) Socket，297MHz，抖，且频率不对 | socket板148.5mhz也抖动无法使用， 最新收到的芯片焊接在主板上的148.5不抖，297抖动，在这个基础上可以正常运行uhd30/fhd60 详细参见No2 sheet | 2025-06-13 socket板在mipi-rx输入端不接IMX415时（生成148.5MHz时）也不会抖。 | 2025-06-19 焊接板在mipi-rx输入端不接IMX415时（生成297MHz时）也不会抖且频率也正确。说明就抖动问题而言，焊接板和socket板的问题性质一样，只是socket板更严重一些 2025-06-20 基于这个，做了个测试，tpgen uhd60,从cchg开始输入，备用分频297M+（4800->440）可以工作的 | 2025-06-20 socket板测量1.1V有肉眼可见的异常。参见No2-sheet 2025-06-20 lyj: 工作过程1.1V电压有点降低，先提高电压测一下。不行再加电容去噪 将1.1V电压提高0.05V后，no.4焊接板，改造以后，297M不抖了，备用分频全频段ok了。No.2 socket改造后，有改善，备用分频148.5 ok了，297还有一点抖，还在确认。 no.2，最后改造与no.4一致了（只做了电压改造），297M还是不稳定，应该还是接触问题，在芯片里垫了点纸片有一些改善，可以出图了，但是有一些不稳定
3 | 2025-06-11 | Close | mipi显示 | uhd30/fhd60使用no.4状态寄存器正确，度信接收size_err错误 | mipi_tx寄存器es2变更后，移植出现了错误，修改后解决。 详细参见No3 sheet
4 | 2025-06-11 | Close | mipi显示 | fhd60 fifo_mon，度信显示异常 | 调整rcc init sequence后正常 详细参见No4 sheet
5 | 2025-06-12 | Close | DIV_NRST | 在rcc switch之后进行DIV reset的话会导致死机，为什么呢？在rcc switch之前则没问题 （但是rcc switch之前进行DIV reset对于解决目前的问题似乎也没有帮助） | div reset导致sys clk丢失。因为div_rstn信号是两个PLL公用，reset的话会导致SYS子系统和datapath子系统的时钟都被停掉。 解决方案：要进行DIV_RSTN时，先将系统侧的时钟切换到27MHz，DIV复位并解除，然后进行系统测时钟的再次切换
6 | 2025-06-12 | Close | mipi显示 | UHD60 4800显示异常 | imx415帧率设置错误，raw设置错误修改后正常 详细参见No5/No6 sheet
7 | 2025-06-12 | Close | 图像显示 | 度信设备上显示的UHD60的帧率不对 | 是受限于PC侧的处理性能，详细参见No7 sheet
8 | 2025-06-13 | OnGoing | timer不稳定 | 无法稳定的产生中断，感觉有丢失 | 详细参见No8 sheet
9 | 2025-06-16 | Close | AF_CLK | 输出给驱动IC用的AF_CLK（DEBUG6）观测不到预期的时钟输出 测试过多个板子，现象相同 | chenxy,2025-06-16 (1) FPGA测试OK，芯片测试与FPGA测试所用软件代码相同 (2) 芯片pad连接的逻辑没有问题(chenql): lisoc.v#1562 PRUW08DGZ_G u_paddebug6 (.I(pwm_clk_o), .OEN(1'b0), .REN(1'b0), .PAD(DEBUG6), .C()); chenql: 封装，引脚等需要检查确认。。。不需要什么外围电路配置，很低频率的时钟 tf:AF0~AF4 GPIO状态正常，拉高拉低符合预期。 | 2025/06/18 debug0~7反了，找到正确对应的引脚，af_clk没问题 Final Solution: 物理数据不动，修改文档中关于映射以及功能描述部分
10 | 2025-06-17 | OnGoing | VCM | DRV201断电后第一次无法通信，LV8498 step设置无效？ | 详细参见No9 sheet
11 | 2025-06-17 | OnGoing | RXTX_THRU | MIPI-RX-TX-Through工作模式测试：度信无法正常接收到图像 | 详细参见No10 sheet | 2025/06/18 FHD60/UHD30 mipi rxtx thru ok了，UHD60有抖动，不知道参数是否还有什么问题，详见\\192.168.1.234\share_LiSoc的视频
12 | 2025-06-17 | OnGoing | TPGEN | 部分节点有问题，无法输出预期的图像 | 详细参见No11 sheet | 2025/06/18 调整了参数后，FHD60/UHD60 三个节点输出一致了，lisr输出最下面有一块绿色，不知道有没有问题
13 | 2025-06-17 | Close | AF_COUNT | AF_COUNT无法计数 | 拉高拉低io，与debug7短接，AF_COUNT计数一直是0，FPGA侧测试ok | 2025/06/19 确认没问题，DBG0对应AF_Count，之前是pwm输入源有问题，重新提供了正确的输入源，计数功能符合预期
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
32
33
34
35
36
37

## ToDo
No. | Description | Remark | Status | Owner

## testcase
No | Casename | Status | Module | Description | Version ID | Result
[5 empty] | ceefcc15c1037d7f76017eff8e1d896865dd1ed1 | PASS

## No1
| EVB No.2 Socket | chip 001/002/007/008
| ES1 |  | ES2
FHD60 | #define D_NMP 1 //rx pix_clk :148.5mhz
#define D_NVC1 1 //video_clk1 :148.5mhz
#define D_NVC2_S1 0x3F
#define D_NVC2_S2 0x04 //video_clk2 :74.25mhz
2
UHD30 | #define D_NMP 0 //rx pix_clk :297mhz
#define D_NVC1 1 //video_clk1 :148.5mhz
#define D_NVC2_S1 0x3F
#define D_NVC2_S2 0x01 //video_clk2 :148.5mhz
寄存器状态错误，无法正确传输图像
测量对应的datapll clock，发现频率出错

## No2
| ES2 |  | ES1
| EVB No.2 (Socket) | chip 001/002/007/008
| video_clk2 148.5mhz |  | 148.5 OK
原分频器 10.125->162M NG
备用分配器 9.267->148.5 抖动
备用分配器 9.267->148.5 抖动
| 备用分配器 18.3->297 抖动 |  | 297 OK
| EVB No.4 (焊接） | chip 004
备用分配器 9.267->148.5 不抖
备用分配器 18.3->297 抖动
2025-06-20 | No2_socket_1v1_imx415_off.mp4(直接插在探测孔里的（比较好量）。lyj:要精确测量，就测电容两端，用探针测)

## No3
addr_0x030寄存器前面需要留8bit的，不然会导致后面的tx参数设置错位。

## No4
对策rcc恢复es1的时序不要等待pll lock，或者初始化完成后加入一些延时，实测加入30ms延时后ok.

## No5
设置错误的地方
1 | 帧率设错了
2 | RAW10宏定义没开
IMX415设置：（1485mbps,只能用10bit）
4400->4800
| reg status: | 显示效果

## No6
UHD60_YUV422_8
video_clk2_324M
原分频器
UHD30_YUV_8
video_clk2_148.5M
备用分频器
FHD60_YUV422_8
video_clk2_74.25M
备用分频器
FHD60_RGB888
video_clk2_74.25M
备用分频器
颜色变绿是调了WB_R_GAIN和WB_B_GAIN
UHD30_RGB888
video_clk2_148.5M
备用分频器
今天uhd30有w_out了，但是不影响显示，不确定是不是与clk不稳定有关系

## No7
pc接收没有瓶颈，主要是接收到的数据转换成图像需要时间，受限于pc的处理性能

## No9
使用树莓派/Rock5B连接DRV201进行寄存器读写
通电
第二次读写OK
再次通电
第二次读写OK
使用lisr连接也遇到了以上问题。
对策是上电后，先进行一次读写，然后重启iic2，再次读写
量测电流，符合预期，可以设置该寄存器，输出从0~102mA。
LV8498没有DRV201的问题，通电后直接可以通信，设置以下寄存器，可以输出0~150mA.
但是这个step设置没什么用，step没有改变.
DRV201可以输出0~102mA
LV8498可以输出0~150mA

## No10
mipi_rxtx_thru
size err，无法出图
UHD60 | FHD60
配置沿用可以正常出图的uhd60/uhd30/fhd60配置,在此基础上打开mipi_rx_tx_thru，度信接收raw10/12格式，无法出图。
关闭这一块设置就ok了
目前UHD60还不行，画面抖动很厉害。

## No11
FHD60_TPGEN |  |  |  | UHD60_TPGEN
TPGEN_SEL： |  |  |  | TPGEN_SEL：
CCHG |  | 寄存器状态不对 |  | CCHG
ISP |  |  |  | ISP | 状态寄存器出错
LISR |  |  |  | LISR
FHD60的ISP和LISR状态比较正常，具体还需要确认输出图像是否正确。
UHD30的CCHG和LISR状态比较正常，具体还需要确认输出图像是否正确。
其他寄存器状态错误，还需要继续调查参数是否设置合理。
2025-06-18
FHD60_TPGEN
#define D_NMP 0 //rx pix_clk: 0,162 1,297 2,324
需要设置0，为什么正常跑用1可以，tpgen需要0
CCHG |  |  | LISOC_TPGEN->addr_0x18.CG_R_E_CCHG = 4095;
LISOC_TPGEN->addr_0x18.CG_R_S_CCHG = 0;
LISOC_TPGEN->addr_0x1C.CG_G_E_CCHG = 4095;
LISOC_TPGEN->addr_0x1C.CG_G_S_CCHG = 0;
LISOC_TPGEN->addr_0x20.CG_B_E_CCHG = 4095;
LISOC_TPGEN->addr_0x20.CG_B_S_CCHG = 0;
LISOC_TPGEN->addr_0x24.PH_CCHG = 0;
LISOC_TPGEN->addr_0x24.PT_CCHG = 0;
LISOC_TPGEN->addr_0x28.ENABLE_CCHG =0;
LISOC_TPGEN->addr_0x18.CG_R_E_CCHG = 4095;
LISOC_TPGEN->addr_0x18.CG_R_S_CCHG = 0;
LISOC_TPGEN->addr_0x1C.CG_G_E_CCHG = 4095;
LISOC_TPGEN->addr_0x1C.CG_G_S_CCHG = 0;
LISOC_TPGEN->addr_0x20.CG_B_E_CCHG = 4095;
LISOC_TPGEN->addr_0x20.CG_B_S_CCHG = 0;
LISOC_TPGEN->addr_0x24.PH_CCHG = 0;
|  |  | LISOC_TPGEN->addr_0x24.PT_CCHG = 1; |  |  | 1和3一样
LISOC_TPGEN->addr_0x18.CG_R_E_CCHG = 4095;
LISOC_TPGEN->addr_0x18.CG_R_S_CCHG = 0;
LISOC_TPGEN->addr_0x1C.CG_G_E_CCHG = 4095;
LISOC_TPGEN->addr_0x1C.CG_G_S_CCHG = 0;
LISOC_TPGEN->addr_0x20.CG_B_E_CCHG = 4095;
LISOC_TPGEN->addr_0x20.CG_B_S_CCHG = 0;
LISOC_TPGEN->addr_0x24.PH_CCHG = 0;
LISOC_TPGEN->addr_0x24.PT_CCHG = 2;
ISP |  |  | LISOC_TPGEN->addr_0x48.CG_R_E_ISP = 4095;
LISOC_TPGEN->addr_0x48.CG_R_S_ISP = 0;
LISOC_TPGEN->addr_0x4C.CG_G_E_ISP = 4095;
LISOC_TPGEN->addr_0x4C.CG_G_S_ISP = 0;
LISOC_TPGEN->addr_0x50.CG_B_E_ISP = 4095;
LISOC_TPGEN->addr_0x50.CG_B_S_ISP = 0;
LISOC_TPGEN->addr_0x54.PH_ISP = 0;
LISOC_TPGEN->addr_0x54.PT_ISP = 3;
LISR |  |  | LISOC_TPGEN->addr_0x78.CG_R_E_LISR = 4095;
LISOC_TPGEN->addr_0x78.CG_R_S_LISR = 0;
LISOC_TPGEN->addr_0x7C.CG_G_E_LISR = 4095;
LISOC_TPGEN->addr_0x7C.CG_G_S_LISR = 0;
LISOC_TPGEN->addr_0x80.CG_B_E_LISR = 4095;
LISOC_TPGEN->addr_0x80.CG_B_S_LISR = 0;
LISOC_TPGEN->addr_0x84.PH_LISR = 0;
LISOC_TPGEN->addr_0x84.PT_LISR = 2;
lisr下面有一块绿色的不知道对不对？
UHD60_TPGEN
CCHG
ISP |  |  | LISOC_TPGEN->addr_0x34.V_OFFSET_ISP = 51; |  |  | 3->51?
改成51 ok了，不然状态寄存器出错，画面闪烁
LISR
| void tpgen_fhd60_init() | void tpgen_uhd60_init()
| { | {
| LISOC_TPGEN->addr_0x00.FRMV_SIZE_CCHG = 1125; | LISOC_TPGEN->addr_0x00.FRMV_SIZE_CCHG = 2250;
| LISOC_TPGEN->addr_0x00.FRMH_SIZE_CCHG = 2400; | LISOC_TPGEN->addr_0x00.FRMH_SIZE_CCHG = 2400;
| LISOC_TPGEN->addr_0x04.V_OFFSET_CCHG = 27; | LISOC_TPGEN->addr_0x04.V_OFFSET_CCHG = 3;
| LISOC_TPGEN->addr_0x04.H_OFFSET_CCHG = 0; | LISOC_TPGEN->addr_0x04.H_OFFSET_CCHG = 0;
| LISOC_TPGEN->addr_0x08.V_OFFSET2_CCHG = 2; | LISOC_TPGEN->addr_0x08.V_OFFSET2_CCHG = 0;
| LISOC_TPGEN->addr_0x0C.TPV_SIZE_CCHG = 1088; | LISOC_TPGEN->addr_0x0C.TPV_SIZE_CCHG = 2176;
| LISOC_TPGEN->addr_0x0C.TPH_SIZE_CCHG = 966; | LISOC_TPGEN->addr_0x0C.TPH_SIZE_CCHG = 1932;
| LISOC_TPGEN->addr_0x10.GSV_SIZE_CCHG = 806; | LISOC_TPGEN->addr_0x10.GSV_SIZE_CCHG = 1612;
| LISOC_TPGEN->addr_0x10.GSH_SIZE_CCHG = 75; | LISOC_TPGEN->addr_0x10.GSH_SIZE_CCHG = 150;
| LISOC_TPGEN->addr_0x14.GSV_START_CCHG = 141; | LISOC_TPGEN->addr_0x14.GSV_START_CCHG = 282;
| LISOC_TPGEN->addr_0x14.GSH_START_CCHG = 70; | LISOC_TPGEN->addr_0x14.GSH_START_CCHG = 141;
| LISOC_TPGEN->addr_0x18.CG_R_E_CCHG = 4095; | LISOC_TPGEN->addr_0x18.CG_R_E_CCHG = 4095;
| LISOC_TPGEN->addr_0x18.CG_R_S_CCHG = 0; | LISOC_TPGEN->addr_0x18.CG_R_S_CCHG = 0;
| LISOC_TPGEN->addr_0x1C.CG_G_E_CCHG = 4095; | LISOC_TPGEN->addr_0x1C.CG_G_E_CCHG = 4095;
| LISOC_TPGEN->addr_0x1C.CG_G_S_CCHG = 0; | LISOC_TPGEN->addr_0x1C.CG_G_S_CCHG = 0;
| LISOC_TPGEN->addr_0x20.CG_B_E_CCHG = 4095; | LISOC_TPGEN->addr_0x20.CG_B_E_CCHG = 4095;
| LISOC_TPGEN->addr_0x20.CG_B_S_CCHG = 0; | LISOC_TPGEN->addr_0x20.CG_B_S_CCHG = 0;
| LISOC_TPGEN->addr_0x24.PH_CCHG = 0; //2bit 0~3 | LISOC_TPGEN->addr_0x24.PH_CCHG = 0;
| LISOC_TPGEN->addr_0x24.PT_CCHG = 0; //2bit 0~3 | LISOC_TPGEN->addr_0x24.PT_CCHG = 0;
| LISOC_TPGEN->addr_0x28.ENABLE_CCHG = 1; | LISOC_TPGEN->addr_0x28.ENABLE_CCHG = 1;
| LISOC_TPGEN->addr_0x30.FRMV_SIZE_ISP = 1125; | LISOC_TPGEN->addr_0x30.FRMV_SIZE_ISP = 2250;
| LISOC_TPGEN->addr_0x30.FRMH_SIZE_ISP = 2200; | LISOC_TPGEN->addr_0x30.FRMH_SIZE_ISP = 2400;
| LISOC_TPGEN->addr_0x34.V_OFFSET_ISP = 27; | LISOC_TPGEN->addr_0x34.V_OFFSET_ISP = 51;
| LISOC_TPGEN->addr_0x34.H_OFFSET_ISP = 0; | LISOC_TPGEN->addr_0x34.H_OFFSET_ISP = 0;
| LISOC_TPGEN->addr_0x38.V_OFFSET2_ISP = 2; | LISOC_TPGEN->addr_0x38.V_OFFSET2_ISP = 0;
| LISOC_TPGEN->addr_0x3C.TPV_SIZE_ISP = 1088; | LISOC_TPGEN->addr_0x3C.TPV_SIZE_ISP = 2176;
| LISOC_TPGEN->addr_0x3C.TPH_SIZE_ISP = 966; | LISOC_TPGEN->addr_0x3C.TPH_SIZE_ISP = 1932;
| LISOC_TPGEN->addr_0x40.GSV_SIZE_ISP = 806; | LISOC_TPGEN->addr_0x40.GSV_SIZE_ISP = 1612;
| LISOC_TPGEN->addr_0x40.GSH_SIZE_ISP = 75; | LISOC_TPGEN->addr_0x40.GSH_SIZE_ISP = 150;
| LISOC_TPGEN->addr_0x44.GSV_START_ISP = 141; | LISOC_TPGEN->addr_0x44.GSV_START_ISP = 282;
| LISOC_TPGEN->addr_0x44.GSH_START_ISP = 70; | LISOC_TPGEN->addr_0x44.GSH_START_ISP = 141;
| LISOC_TPGEN->addr_0x48.CG_R_E_ISP = 4095; | LISOC_TPGEN->addr_0x48.CG_R_E_ISP = 4095;
| LISOC_TPGEN->addr_0x48.CG_R_S_ISP = 0; | LISOC_TPGEN->addr_0x48.CG_R_S_ISP = 0;
| LISOC_TPGEN->addr_0x4C.CG_G_E_ISP = 4095; | LISOC_TPGEN->addr_0x4C.CG_G_E_ISP = 4095;
| LISOC_TPGEN->addr_0x4C.CG_G_S_ISP = 0; | LISOC_TPGEN->addr_0x4C.CG_G_S_ISP = 0;
| LISOC_TPGEN->addr_0x50.CG_B_E_ISP = 4095; | LISOC_TPGEN->addr_0x50.CG_B_E_ISP = 4095;
| LISOC_TPGEN->addr_0x50.CG_B_S_ISP = 0; | LISOC_TPGEN->addr_0x50.CG_B_S_ISP = 0;
| LISOC_TPGEN->addr_0x54.PH_ISP = 0; | LISOC_TPGEN->addr_0x54.PH_ISP = 0;
| LISOC_TPGEN->addr_0x54.PT_ISP = 3; | LISOC_TPGEN->addr_0x54.PT_ISP = 2;
| LISOC_TPGEN->addr_0x58.ENABLE_ISP = 1; | LISOC_TPGEN->addr_0x58.ENABLE_ISP = 1;
| LISOC_TPGEN->addr_0x60.FRMV_SIZE_LISR = 1125; | LISOC_TPGEN->addr_0x60.FRMV_SIZE_LISR = 2250;
| LISOC_TPGEN->addr_0x60.FRMH_SIZE_LISR = 2200; | LISOC_TPGEN->addr_0x60.FRMH_SIZE_LISR = 2400;
| LISOC_TPGEN->addr_0x64.VSW_LISR = 5; | LISOC_TPGEN->addr_0x64.VSW_LISR = 5;
| LISOC_TPGEN->addr_0x64.HSW_LISR = 22; | LISOC_TPGEN->addr_0x64.HSW_LISR = 22;
| LISOC_TPGEN->addr_0x68.VFRBLK_LISR = 41; | LISOC_TPGEN->addr_0x68.VFRBLK_LISR = 41;
| LISOC_TPGEN->addr_0x68.HFRBLK_LISR = 96; | LISOC_TPGEN->addr_0x68.HFRBLK_LISR = 96;
| LISOC_TPGEN->addr_0x6C.TPV_SIZE_LISR = 1080; | LISOC_TPGEN->addr_0x6C.TPV_SIZE_LISR = 2160;
| LISOC_TPGEN->addr_0x6C.TPH_SIZE_LISR = 960; | LISOC_TPGEN->addr_0x6C.TPH_SIZE_LISR = 1920;
| LISOC_TPGEN->addr_0x70.GSV_SIZE_LISR = 800; | LISOC_TPGEN->addr_0x70.GSV_SIZE_LISR = 1600;
| LISOC_TPGEN->addr_0x70.GSH_SIZE_LISR = 74; | LISOC_TPGEN->addr_0x70.GSH_SIZE_LISR = 149;
| LISOC_TPGEN->addr_0x74.GSV_START_LISR = 140; | LISOC_TPGEN->addr_0x74.GSV_START_LISR = 280;
| LISOC_TPGEN->addr_0x74.GSH_START_LISR = 70; | LISOC_TPGEN->addr_0x74.GSH_START_LISR = 140;
| LISOC_TPGEN->addr_0x78.CG_R_E_LISR = 4095; | LISOC_TPGEN->addr_0x78.CG_R_E_LISR = 4095;
| LISOC_TPGEN->addr_0x78.CG_R_S_LISR = 0; | LISOC_TPGEN->addr_0x78.CG_R_S_LISR = 0;
| LISOC_TPGEN->addr_0x7C.CG_G_E_LISR = 4095; | LISOC_TPGEN->addr_0x7C.CG_G_E_LISR = 4095;
| LISOC_TPGEN->addr_0x7C.CG_G_S_LISR = 0; | LISOC_TPGEN->addr_0x7C.CG_G_S_LISR = 0;
| LISOC_TPGEN->addr_0x80.CG_B_E_LISR = 4095; | LISOC_TPGEN->addr_0x80.CG_B_E_LISR = 4095;
| LISOC_TPGEN->addr_0x80.CG_B_S_LISR = 0; | LISOC_TPGEN->addr_0x80.CG_B_S_LISR = 0;
| LISOC_TPGEN->addr_0x84.PH_LISR = 0; | LISOC_TPGEN->addr_0x84.PH_LISR = 0;
| LISOC_TPGEN->addr_0x84.PT_LISR = 2; | LISOC_TPGEN->addr_0x84.PT_LISR = 2;
| LISOC_TPGEN->addr_0x88.ENABLE_LISR = 1; | LISOC_TPGEN->addr_0x88.ENABLE_LISR = 1;
| } | }

## No12
UHD60_RAW10_YUV422_8
dbg0 | dbg7(AF_Count)
dbg1 | dbg6(AF_CLK)
dbg2 | dbg5(NUM1)
dbg3 | dbg4(NUM0)
dbg4 | dbg3(LV)
dbg5 | dbg2(FV）
dbg6 | dbg1(HD)
dbg7 | dbg0(VD)

## No13
DQ16
apb_wr_cmd(reg_channel_en,3);
LISOC_LISR->addr_0xF8.DDR16MODE = 1;
Interlace
mipi lane swapping
#define D_DPHY_P0_TX_LP11 3
#define D_DPHY_P0_TX_LP10 2
#define D_DPHY_P0_TX_LP01 1
#define D_DPHY_P0_TX_LP00 0
DPHY_P0_TX_LP11/LP10/LP01/LP00 | 图像显示状态
1230 | NG
1203 | OK
1320 | NG
1302 | NG
1023 | OK
1032 | NG
2130 | NG
2103 | OK
2301 | NG
2310 | NG
2013 | OK
2031 | OK
3120 | NG
3102 | NG
3201 | NG
3210 | OK
3012 | OK
3021 | OK
123 | OK
132 | NG
231 | OK
213 | OK
321 | NG
312 | NG